## Slide 1: Strategic Planning 2010-2011
Save these dates!
October 14, 15 and 16, 2010
ASU Student Union
Planning for ASU’s Next Century

## Slide 2: Strategic Planning Through Open Space Technology
Participants “create the agenda”
Participants must commit to the entire 2.5 days
Open Space Technology: A User's Guide, by Harrison Owen. Berrett-Koehler Publishers; 3rd edition April 1, 2008.
Limited copies available in the Dean B. Ellis Library

## Slide 3: Projected Strategic Planning Time Line Phase 1
Campus-Wide Strategic Planning Event: Oct. 2010
Preparation of Initial Draft of Strategic Plan:
Oct. - Dec. 2010
Campus Review of Draft Strategic Plan: Jan.- Feb. 2011
Strategic Plan Revised Based on Campus Comments:
Feb.- Mar. 2011
Strategic Plan Reviewed by Chancellor and
Executive Council: Mar.- Apr. 2011
Strategic Plan Reviewed by President and
Board of Trustees: April 2011
Board of Trustees Approval: May 2011

## Slide 4: Phase 2
Strategic Plan Action Steps Developed in Support of
5 HLC Criteria: June-Oct. 2011
Action Steps Reviewed/Revised by Units (Academics, Finance, Student Affairs, etc.): Oct.-Dec. 2011
HLC/Strategic Plan Self Study Draft Prepared:
Jan.-Mar. 2012
Self Study Reviewed by Chancellor and
Executive Council: May-June 2012
Self Study Submitted to HLC Review Team: Aug. 2012
Self Study Draft Reviewed by Units and Revised:
Mar.-May 2012
Final Revisions of Self Study and Approval
by Chancellor: June-Aug. 2012