## Priority 1
Strategic Plan Action Steps 2011-2015 |  | DRAFT 12-12-12
Division: Academic Affairs and Research
Priority 1. Refine ASU’s mission and identity as an emerging global research institution.
Goal 1A. Pursue Appropriate Carnegie Classification Based on Role and Scope
Goal 1B. Continue to Promote Teaching and Learning Endeavors That Are Integral to a Global Research Institution
Goal 1C.Continue to Promote the Transformation of ASU Into a Research-Intensive Institution
Goal 1D. Promote Outcome-Based Decision Making
Goal 1E. Increase Undergraduate and Graduate Enrollment of Well-Qualified Students
Goal | Action Steps | Timeline | Resources | Target Audience | Measurable Outcomes | Responsible Party | Status
1A.1 | Place the University on a trajectory to become classified as a Doctoral Research University (Carnegie) and an SREB Four-Year 2 institution within the next five years by increasing the number of doctoral graduates to an average of 20 per year from the current rate of 12.5 per year by: | 2011-2016 | Human Resources |  | Doctoral graduate increases of 20 per year Carnigie/30 per year SREB | Deans and Program Directors | In Progress
1A.2 | Develop a strategic plan for every doctoral program with an emphasis on student recruitment, retention, and graduation; | Jan. 15, 2012 | Human Resources |  | Increased Doctoral Students | Deans | In Progress
1A.3 | Ensure that all existing doctoral programs are funded appropriately; | Spring 2012 | Reallocation within AAR |  | Increased number of Doctoral Graduates | Provost & AAR | In Progress
1A.4 | Develop stronger incentive structures that will encourage more faculty to serve as mentors for doctoral students; | Fall 2012 | Budgetary commitment for faculty stIpends |  | Increased number of Doctoral Graduates | Provost, Deans | In Progress
1A.5 | Identify and introduce new low-cost, high-demand doctoral programs that are consistent with the university’s mission; | Identify by Fall 2012 and implement as appropriate | Allocated as needed |  | Increased number of Doctoral Graduates | Provost, Deans | In Progress
1A.6 | Develop a strong institutional pIn Progresseline for each doctoral programs by offering tuition waivers for all master’s level graduate students; | Spring 2012 | Institutional | Graduate Students | Increased number of Doctoral Graduates | Provost | In Progress
1A.7 | Develop a strategic recruitment and communications plan for the Graduate School that utilizes the full capabilities of the Hobson’s software system; | Jan. 15, 2012 | Human Resources and Purchase of Software |  | Increased number of Doctoral Graduates | Graduate Dean | Hobson's Software Purchased Oct. 2011
1A.8 | Increase the number of graduate assistant stIn Progressends available in addition to increasing the dollar amount of such stIn Progressends; | Spring 2012 | Instituional Budget | Graduate students | Increased number of Doctoral Graduates | Provost. Graduate Dean | In Progress
1A.9 | Support the continued growth of the Honors College by offering more Honors courses; developing an incentive structure for departments/faculty that offer Honors courses; and allocate additional human resources in order to meet the needs of this growing population within the student body. | Fall 2012 | AAR Budget | Honors Students | Increased number of honors students | Provost/ Honors Dean | Position Allocated to Honors Fall 2011
1B.1 | Pursue the creation of dual tenure-track systems in all departments to maintain teaching quality while expanding the number of faculty who particIn Progressate in research activities. | Spring 2012- Fall 2013 | Human Resources | Faculty | Teaching Quality and Enhanced Research Activitey | Provost, Deans, Chairs | In progress
1B.2 | Where possible, offer more large-enrollment courses to enable a larger number of faculty to engage in research activities. | Fall 2012 | Allocation of GTAs |  | Enhanced Research Activity | Deans, Chairs | In progress
1B.3 | Pursue placing at least tHuman Resourcesee new degree programs online during 2011 in an effort to accommodate student demand and to enable a greater number of faculty to particIn Progressate in research-related endeavors. | 2011-2012 |  |  | Programs of MPA, BSIS and RN-BSN, Gifted & Talented, EDS | AVCAS, Deans, Chairs | Completed and In Progress
1B.4 | Work with the deans and department chairs to survey all academic programs to determine which courses or programs are feasible to offer in an online format. | Spring-Summer 2012 |  |  | All applicable programs feasible for on-line delivery are prepared or in preparation for timely launch for on-line delivery | Deans, Chairs | In Progress
1C.1 | Continue to grow all research indicators by at least 10% each year. These indicators include competitive research expenditures, the number and dollar amount of competitive research awards, the number and dollar value of research proposals, F&As generated, and similar indicators for other sponsored program activity. | 2011-2016 | F&A Resources |  | 10% per gorwth in each research measure | Vice Provost-Research | In Progress
1C.2 | Develop a formal framework for prospective Centers of Excellence. This framework will include the purpose, expectations, management, and support. | 2011-2012 |  |  | Completed framework | Vice Provost-Research, Provost | In Progress - Three Centers up and running, four including ABI.
1C.3 | Introduce at least one Center of Excellence each year with the goal of having the center become self-sustaining within a five-year period of time. | 2012-2016 |  |  | Addition of one new Center of Excellence each year; each center self-sustaining at end of five years of existence | Vice Provost-Research, Provost | In Progress - Three Centers up and running, four including ABI.
1C.4 | Capture the global aspects of research opportunities for students and faculty by doing a better job of “Telling Our Story” by sharing past research successes and the many research and research-related initiatives that are currently underway or that will be launched in the near future. | 2011-2016 |  | Graduate Students, Community, Funding Agencies | MeASUre , other publications, PR | Vice Provost-Research, Provost, | In Progress - third edition of MeASUre in print August 2013
1C.5 | Develop and maintain a comprehensive system for tracking award and expenditure activity for all sponsored programs awards. | 2011-2016 |  | Faculty | Implemented Banner Application | Vice Provost-Research | In Progress - CAYUSE still in use. ORTT/SPA joint effort needed on this.
1D.1 | Allocate/reallocate resources in a manner that best supports the university’s transition to research-intensive status, currently and in the future. [Direct resources to high-enrollment, high-growth, and research-intensive programs while holding units accountable for productivity.] | 2011-2016 | Allocation of new resources as available and reallocation of exisiting resources to promote outcomes | Faculty and Research Units | Stronger students, quality teaching, increased research, continued accreditation, service to community | AAR | In Progress
1D.2 | Continue to comply with all state regulations in budgetary matters and ending fiscal year with a positive fund balance. | 2011-2016 |  | AAR Units | Compliance and favorable audit outcome | Provost | In Progress
1E.1 | The Graduate School will collaborate with all graduate programs in developing a recruitment and communications plan in addition to an applicant tracking system to ensure targeted recruitment efforts are successful. | 2011-2012 |  | Graudate Students | Increased enrollment of well qualified students | Graduate Dean, Deans | In Progress
1E.2 | College deans, department chairs, program directors, and the faculty will support the continuing efforts of the Office of Admissions by participating in Preview Days, Honors Day, and other special events designed to attract well-qualified students to ASU. | 2011-2016 |  | Students | Increased enrollment of well qualified students | Provost, Deans, Chairs, Directors | In Progress
1E.3 | Continue to develop and offer academic programs of interest to potential students. | 2011-2016 |  | Students | Continued enrollment increases; viable academic programs | Provost, Deans, Chairs, Directors | In Progress Undergraduate completed
1E.4 | Enrollment management plans at the undergraduate and graduate levels will be reviewed and updated by the conclusion of academic year 2011-2012. | 2011-2012 |  | Students | Up-dated enrollment management plans | Provost, AVCAAS, Graduate Dean | In Progress

## Priority 2
Strategic Plan Action Steps 2011-2015 |  | DRAFT 12-12-12
Division: | Academic Affairs and Research
Priority 2. Create a Service and Support Culture that is Focused on Student Learning, Retention, and Academic success.
Goal 2A. Place the Student Learning Experience as the Central Focus of Teaching
Goal 2B. Review Relevancy of General Education Program
Goal 2C. Continue to Develop a Culture of Assessment to Enhance Learning Outcomes
Goal 2D. Enhance Student Persistence and Academic Success
Goal 2E. Manage the Use of Financial Aid to Help Attract and Retain Students
Goal 2F. Provide Opportunities to Better Understand Student Needs
Goal | Action Steps | Timeline | Resources | Target Audience | Measurable Outcomes | Responsible Party | Status
2A.1 | The Office of the Provost will work collaboratively with the campus community in re-establishing the Faculty Center on the campus of ASU. The new center will focus on equipping faculty with the skills. | Spring 2012 | Reallocated from within AAR | Faculty | Implementation of Faculty Center | Provost | In Progress
2A.2 | The Quality Teaching Circle and Learning Initiative will be expanded to include all tenure-track faculty and non-tenured instructors. | Fall 2011 |  | Faculty | Enhanced instruction and learning. | Provost, Diversity | In Progress; Fall 2011 sessions included invitation to appropraite faculty
2A.3 | Collaborate with Facilities Management and ITS on a classroom renovation initiative designed to develop state-of-the art learning environments that facilitate student learning and the utilization of appropriate technology. | Summer 2011-2016 | Reallocated | Students, Faculty | Enhanced instrucgtion and learning | Provost, Facilities | In progress; Improvements made to Wilson Hall, Communications, Lab Sciences, Engineering 2011
2A.4 | Define and create a culture of customer service and student support. | Fall 2012 |  | Faculty, Staff | Improved customer service in academic units; enhanced student support within and among academic units | Provost, Deans, Chairs, Directors | In Progress
2B.1 | The Associate Vice Chancellor for Academic Services will lead a discussion among General Education committee members concerning the number of hours required in the Gen. Ed. Core, the nature and purpose of currently-required courses, in addition to the changes that will be necessary to comply with the state’s mandate that all baccalaureate degree programs be limited to 120 hours unless licensure or accreditation requirements dictate otherwise. | Fall 2011 |  | General Education Faculty; Academic Programs | Revised General Education Curriculum to support reduction of bachelor level degree programs to 120 hours | AVCAS, General Education Committee Chair and Members | In Progress - General Education Curriculum recommended to follow state core of 35 hours Nov. 2011; in SG review
2B.2 | A comparative analysis will be conducted to compare ASU’s general education offerings with those of its peers. | Spring 2011-Fall 2012 |  | General Education Committee | Comparison completed and indicated that most peer institutions had reduced general education core or were in process of reducing to state miniumum core | AVCAS, General Education Committee Chair and Members | Completed
2C.1 | Work with the University’s Promotion, Retention, and Tenure Committee to identify ways in which assessment can be incorporated into the faculty rewards structure. | Spring 2012 |  | Faculty | Assessment of student learning outcomes valued as part of PRT process by inclusion in PRT standards. | Provost, AVCAS | In Progress
2C.2 | Continue to support and expand the work of the Office of Student Learning Outcomes Assessment by providing administrative support and a permanent office location for the daily activities of the office. | Fall 2011-Spring 2012 | Reallocation within AAR | Assessment Director | Permanent Office of Student Learning Outcomes Assessment with adequate staff and support. | Provost, AVCAS | Clerical Support added summer 2011; permanent space identified
2C.3 | Continue to monitor the progress that is being made with the University’s assessment plan and the General Education assessment plan in preparation of the reaffirmation visit of the Higher Learning Commission. |  |  | Students, Faculty | Regular progress reports on assessment initiatives and data. | Provost, AVCAS, Director of Assessment; General Education Committee; University Assessment Committee | In Progress
2C.4 | Promote and publish campus best practices in assessment via a quarterly publication/website and an annual mini-conference on assessment. |  |  | Faculty | Regular progress reports on assessment initiatives, data and accomplishments. | Provost, AVCAS, Director of Assessment | In Progress - Assessment website with selected accomplishments
2D.1 | Move all developmental courses under University College to provide our most academically challenged students with an environment designed to build core academic skills (math, writing, reading) that many of our students are sorely lacking. | Fall 2011 |  | Development al Education Students and Associated Faculty | All developmental courses reside in University College First Years Students Department supported by common goals for developmental education success. | Provost, AVCAS, Director of First Year Studies | Completed
2D.2 | Conduct an analysis of pass/fail rates of high-enrollment, mandatory courses to determine if certain courses are de facto “gate-keeper” courses, thereby serving as a limiting factor to student persistence and graduation. | 2011-2012 |  | Students, Faculty | Identification of "gate-keeper" courses. | Provost, AVCAS; Retention Committee | In Progress
2D.3 | Collaborate with University Advancement to raise philanthropic funds to support scholarships for students in hopes of alleviating the primary obstacle to student persistence and graduation – financial resources. | 2011-2016 |  | Students | Increased scholarship opportunities for students and imporved graduation rate. | Provost | In Progress
2D.4 | Continue recognizing the importance of proper advising and incorporating advising into the rewards structure for faculty. | 2012-2016 |  | Students, Faculty | Approval to raise level of Advising Award to that of other faculty awards of teaching, research and service. | Provost, AVCAS | In Progress
2D.5 | Effective with the onset of the fall 2011 semester, members of ASU’s Wilson Advising Center will monitor the progress of undergraduate students (particularly freshmen) and will take actions to provide special counseling and assistance. | 2011-2016 |  | Students | Increased student success and retention. | AVCAS, UC Dean, Director of Wilson Advising Center | In Progress; Expanded Early Alert System
2D.6 | A comprehensive plan will be devised to assess all aspects of the Academic Success Institute (ASI) and this plan will be implemented during the academic year 2011-2012 with associated data collected, analyzed, and used to inform decisions as to continuous quality improvement of the ASI. | 2011-2012 |  | Students, ASI Faculty | Increased success of ASI students. | AVCAS, UC Dean, Director of First Year Studies | In Progress; Anyalysis of 2010-2011 completed; revisions made in program for fall 2012
2D.7 | Commencing with the fall semester 2010, the Office of the Registrar, with assistance from other university units such as Admissions and Financial Aid, will monitor pre-registration and registration of current students and will follow-up by e-mail and telephone calls with any students who do not register for the ensuing semester to help them resolve any/all barriers to their continuing of academic studies at ASU in order to improve student retention and graduation rates. | 2010-2016 |  | Students | Increased enrollment and retentionl | Provost, AVCAS, Registrar | In Progress
2D.8 | Commencing with the fall semester 2010, the Office of the Registrar will communicate by e-mail and telephone calls with all students who failed to return to ASU before degree completion to encourage them to return to complete their academic program and to offer a wide array of support services in an effort to increase graduation rates. | 2010-2016 |  | Students | Increased graduation rate. | Provost, AVCAS, Registrar | In Progress
2E.1 | Administer, publish, and discuss the results of the National Survey of Student Engagement with faculty and students every three years. Use data to implement change. | 2011-2016 |  | Students, Faculty, Staff | Enhanced understanding of student engagement. | Provost, AVCAS, Director of Institutional Research, Director of Assessment | In Progress
2E.2 | Continue to provide meaningful student participation in AARC and the development of spending plans related to the student infrastructure and technology fees. | 2011-2016 |  | Students | Enhanced understanding of student academic needs associated with use of Infrastructure and technology fees. | Provost | In Progress
2E.3 | The Provost will host a formal meeting of student leaders each semester to learn more about their educational experiences at ASU. | 2011-2016 |  | Students | Enhanced understanding of student statisfaction and concerns. | Provost, AVCAS | In Progress; Fall 2011 meeting with SGA

## Priority 3
Strategic Plan Action Steps 2011-2015 |  | DRAFT 12-12-12
Division: | Academic Affairs and Research
Priority 3. Create learning experiences through student engagement, service to our region, and partnerships with our community.
Goal 3A. Increase Service-Learning and Community Engagement Opportunities
Goal 3B. Enhance Community Outreach
Goal 3C. Promote Safety, Environmental Responsibility, and Stewardship
Goal | Action Steps | Timeline | Resources | Target Audience | Measurable Outcomes | Responsible Party | Status
3A.1 | A survey will be conducted of all service-learning initiatives currently underway at ASU. | 2011-2012 |  | Campus and Community | Comprehensive inventory of service learning initiatives. | HLC Subcommittee; Dean of CECO | In Progress; Survey conducted Fall 2011
3A.2 | The results of the survey will be published to the campus community. | 2011-2012 |  | Campus and Community | HLC Self-Study and Campus Inventory | HLC Self-Study Committee | In Progress
3A.3 | Utilizing the items listed above and after collaborating with the campus community, determine the extent to which the University will engage in service-learning and community engagement opportunities. | 2011-2016 |  | Campus and Community | Increase in service-learning opportunities for students. |  | In Progress
3A.4 | Consultants will be retained to assist the faculty in incorporating service-learning experiences into their courses and promoting the importance of these experiences to the student body. | 2012-2014 | Reallocation within AAR | Faculty, Students, Community | Increased service-learning initiatives within academic programming. |  | In Progress
3A.5 | Document and report all service-learning and community engagement activities on an annual basis. | 2011-2016 |  | Campus Community | Current inventory of service-learning actitivies. | Provost, Deans, Chairs, Directors | In Progress
3B.1 | Survey colleges and departments to determine the extent to which faculty are engaged in community outreach activities via professional service, grant activities, or scholarship activities. | 2012 |  | Academic Departments and Colleges | Inventory of faculty utilization of service-leraning in academic curriculum. | Provost, HLC Self-Study Committee | In Progress
3B.2 | Develop a comprehensive plan to expand the range of programmatic offerings housed in CECO. | 2011-2012 |  | Campus and Community | Long-term plan for CECO programming. | Provost, Dean of CECO | In Progress
3B.3 | Survey our community constituents to identify opportunities for new or enhanced engagement by the University, including both credit and non-credit bearing activities. | 2012 |  | Campus and Community | Established list of community interests for current and future programmming. | Provost, Dean of CECO | In Progress

## Priority 4
Strategic Plan Action Steps 2011-2015 |  | DRAFT 12-12-12
Division: | Academic Affairs and Research
Priority 4. Create a collaborative decision-making environment that is based on effective shared governance, open communication, and mutual respect of all members of our teaching and learning community.
Goal 4A. Develop a Sense of Campus Community
Goal 4B. Create Transparency in Planning and Decision-Making
Goal | Action Steps | Timeline | Resources | Target Audience | Measurable Outcomes | Responsible Party | Status
4A.1 | AAR and all of its units will continue to embrace the tenets of shared governance by remaining collaborative and transparent in all decisions. | 2011-2016 |  | Faculty, Staff and Students | Increased understanding and satisfaction of shared governance process. | All AAR Administration, Faculty and Staff | In Progress
4A.2 | AAR will continue to follow established processes and engage appropriate constituency groups when making decisions that will impact the campus and faculty. | 2011-2016 |  | Faculty, Staff and Students | Increased understanding and satisfaction of shared governance process. | All AAR Administration, Faculty and Staff | In Progress
4A.3 | Provost will introduce “Conversations With the Provost” in early October to provide an opportunity to discuss the activities in AAR in an intimate setting with faculty and academic staff. | 2011-2016 |  | Faculty, Staff and Students | Increased understanding and satisfaction of shared governance process and ehanced understanding of the role and responsbilities of AAR. | Provost and AAR Senior Staff | In Progress; Fall 2011 meetings held with new faculty, SGA
4A.4 | Provost will work with Executive Council to identify mechanisms for developing a sense of Campus Community. | 2011-2016 |  | Faculty, Staff and Students | Increased understanding and satisfaction of shared governance process. | Provost

## Priority 5
Strategic Plan Action Steps 2011-2015 |  | DRAFT 12-12-12
Division: | Academic Affairs and Research
Priority 5. Adopt policies and models that continuously promote, grow and reward all modes of effective teaching and learning experiences.
Goal 5A. Support and Reward Multiple Modalities of Teaching and Learning
Goal 5B. Refocus on Excellence in Teaching and Learning
Goal | Action Steps | Timeline | Resources | Target Audience | Measurable Outcomes | Responsible Party | Status
5A-B.1 | During the 2011-2012 academic year, AAR will reintroduce a comprehensive Center for Excellence in Teaching/Instructional Innovation designed to support, encourage, and reward multiple modalities of teaching and learning. | Fall 2011-Spring 2012 | Realloacted from AAR | Faculty | Implementation of Teaching Center | Provost | In Progress; plans for center operation and renovation of 3rd floor library space drafted
5A-B.2 | During the 2011-2012 academic year, AAR will work with the ITTC to hire an Instructional Designer to assist faculty in the design, development, and delivery of both traditional and online courses and programs. | Spring 2012 | Exisiting | Faculty | Instructional Designer hired | Provost, Director of ITTC | In Progress
5A-B.3 | During the 2011-2012 academic year, AAR will establish a vehicle for publishing and rewarding campus best teaching practices. | Spring 2012 |  | Faculty | Publication and teaching recongition process developed. | Provost, Director of ITTC | In Progress
5A-B.4 | During the 2011-2012 academic year, AAR will introduce a publication that highlights outstanding teaching by capturing exceptional performances in the classroom. | Spring 2012 |  | Faculty | Publication produced highlighting exception teaching | Provost, Director of ITTC | In Progress

## Priority 6
Strategic Plan Action Steps 2011-2015 |  | DRAFT 12-12-12
Division: | Academic Affairs and Research
Priority 6. Increase our diversity and expand our globalization.
Goal 6A. Prepare Students for Global Citizenship
Goal 6B. Develop a Service Environment that Supports the Needs of a Diverse ASU Community
Goal 6C. Attract, Employ, Retain, and Advance Greater Numbers of University Faculty and Staff from Underrepresented Groups
Goal | Action Steps | Timeline | Resources | Target Audience | Measurable Outcomes | Responsible Party | Status
6A-C | Develop a new, comprehensive five-year diversity plan that focuses on: (1) preparing students for global citizenship, (2) developing an infrastructure that supports the needs of a diverse community, and (3) attracting, employing, retaining, and advancing greater numbers of university staff from underrepresented groups. | [5 empty] | In Progress
6A.1 | Develop a plan to provide academic opportutintes to prepare students for global citizenship through currciular initiatives integrated in the first year and beyond. | 2011-2016 | Reallocated and New | Students | Graduates with a greater understanding of diverse communities and global citizenship. (Charge from General Education Committee) | Provost, Acaedmic Units | In Progress
6B.1 | Support the needs of a diverse community through developing a plan to determine the service related needs of students, faculty and staff from diverse backgrounds. | 2012 |  | Students, Faculty and Staff | Increased satisfaction of support service initiatives and customer service associated with the diverse campus community. | Provost, Acaedmic Units | In Progress
6C.1 | Utilize the diversity plan for attracting, employing, retaining, and advancing greater numbers of university faculty and staff from underrepresented groups. | 2011-2016 |  | Faculty and Staff | Increased rate of recruitment, retention and advancement of diverse faculty and staff. | Provost, Acaedmic Units | In Progress

## Priority 7
Strategic Plan Action Steps 2011-2015 |  | DRAFT 12-12-12
Division: | Academic Affairs and Research
Priority 7. Continually improve our institutional efficacy and alignment of resources with our priorities.
Goal 7A. Enhance Recruitment and Retention Initiatives of Faculty and Staff
Goal 7B. Maintain Current and Strategically Plan for Future Infrastructure Needs
Goal 7C. Expand Resources and Refine Budget Procedures
Goal | Action Steps | Timeline | Resources | Target Audience | Measurable Outcomes | Responsible Party | Status
7A.1 | Utilize Diversity Plan to support recrutiment and retention of faculty and staff. | 2011-2016 |  | Faculty and Staff | Increased retention of faculty and staff. | Provost, Academic Units | In Progress
7B.1 | Utilize Campus Master Plan in association with strategic plan . | 2012-2016 |  |  | Improved efficacy and alignment of resources with institutional priorities. | Provost, Academic Units | In Progress
7C.1 | Serve as good stewards of existing resources and utilize mechanisms in plan for making sound budgetary decisions. | 2011-2016 |  |  | Improved efficacy and alignment of resources with institutional priorities. | Provost, Academic Units | In Progress